TAKTFLOW SDV PLATFORM Gap Filling Plan Systematic closure of all identified gaps from prototype to production-ready open-source HIL Gaps Identified 12 total; Critical (P1) 3 gaps; Total Effort ~24 weeks; After Closure 90%+ CANoe parity.

# 1. Overview

This document tracks all identified gaps in the Taktflow SDV platform against the target state of a production-ready, vendor-portable, ASIL D-capable open-source HIL. Each gap has a unique ID, priority, root cause, impact, fix path, tooling, effort estimate, and reusability assessment.

The current platform state is strong: 7-ECU mixed HIL running, ARXML strict validation passing, SIL automated. The gaps below are the delta between the working prototype and a platform that a Tier-1 supplier or engineering services company could use commercially.

Reusability is a first-class concern. Every gap fix is evaluated for whether it produces a reusable module — slave firmware, pytest fixture, CI step, or generator — that amortizes the effort across future projects. Gaps where the fix is not reusable are deprioritized.

# 2. Gap Summary

| ID | Layer | Title | Priority | Effort | Status | Reusable |
| --- | --- | --- | --- | --- | --- | --- |
| GAP-01 | L0 — Requirements | ReqIF Requirements Layer | P1 — Critical | 1 week | Gap | ✓ Yes |
| GAP-02 | L2 — ARXML | ARXML XSD Validation in CI | P1 — Critical | 2 days | In Progress | ✓ Yes |
| GAP-03 | L5 — PIL | PIL Transport Adapter | P1 — Critical | 1 week | Gap | ✓ Yes |
| GAP-04 | L3 — BSW Codegen | Os_Cfg / NvM_Cfg / WdgM_Cfg Generators | P2 — High | 2–3 weeks | Planned | ✓ Yes |
| GAP-05 | L6 — HIL | XCP Measurement & Calibration | P2 — High | 5–7 weeks | Planned | ✓ Yes |
| GAP-06 | CI / Quality | SonarQube / SonarCloud Dashboard | P2 — High | 2–3 days | Planned | ✓ Yes |
| GAP-07 | L6 — HIL | LIN Restbus Simulation | P2 — High | 2–3 weeks | Planned | ✓ Yes |
| GAP-08 | L1 — System Model | Capella MBSE System Model | P3 — Medium | 3–4 weeks | Planned | ✓ Yes |
| GAP-09 | L6 — HIL | Automotive Ethernet / DoIP | P3 — Medium | 2–3 weeks hardware + software | Planned | ✓ Yes |
| GAP-10 | CI / Quality | MC/DC Coverage for ASIL D | P3 — Medium | 1–2 weeks | Planned | ✓ Yes |
| GAP-11 | L3 — BSW Codegen | A2L / DCM Calibration File Generation | P4 — Low | 2–3 weeks (partly overlaps GAP-05) | Planned | ✓ Yes |
| GAP-12 | Docs / Portfolio | Public GitHub Repository + Demo Video | P4 — Low | 1 week | Planned | N/A — one-time documentation effort |

# 3. Gap Details

| GAP-01 | ReqIF Requirements Layer | P1 — Critical | Gap |
| --- | --- | --- | --- |

| Layer | L0 — Requirements |
| --- | --- |
| Problem | No requirements.reqif file exists. Traceability scripts (gen-traceability.sh, suspect-links.py) have nothing to link against. Test cases have no requirement ID references. Polarion / IBM DOORS import is not possible. |
| Impact | Cannot demonstrate requirement-to-test traceability. Breaks ISO 26262 ASIL D evidence chain. Portfolio cannot claim end-to-end traceability without this layer. |
| Fix | Create reqif/ folder. Define ~50 baseline requirements covering CAN communication, safe state behavior, fault detection, and E2E protection. Assign REQ-IDs to existing pytest test cases. Run gen-traceability.sh to produce first coverage report. |
| Tools | doorstop (git-native), ReqIF 1.2 XML, gen-traceability.sh (already exists) |
| Effort | 1 week ¦ Reusable: Yes — req IDs and traceability framework reused per project |

| GAP-02 | ARXML XSD Validation in CI | P1 — Critical | In Progress |
| --- | --- | --- | --- |

| Layer | L2 — ARXML |
| --- | --- |
| Problem | ARXML strict schema validation passes in prototype (autosar-data: 0 warnings, 0 errors) but is not yet a hard CI gate. A future commit could silently break schema compliance. |
| Impact | DaVinci / EB tresos import could break without anyone noticing. The current pass result is a snapshot, not a guarantee. |
| Fix | Add validate_arxml.py as a mandatory CI step in GitHub Actions. Exit code 1 on any strict violation or reference error. Add armodel round-trip check with delta threshold ≤20. |
| Tools | autosar-data 0.10.x, armodel 1.8.x, GitHub Actions (already configured) |
| Effort | 2 days ¦ Reusable: Yes — same CI step works for every ARXML-generating project |

| GAP-03 | PIL Transport Adapter | P1 — Critical | Gap |
| --- | --- | --- | --- |

| Layer | L5 — PIL |
| --- | --- |
| Problem | pytest --target=pil flag exists in design but the conftest.py transport fixture is not wired. Same test cases must run on real silicon (STM32H7 / TMS570) via OpenOCD semihosting without code change. |
| Impact | SIL → PIL parity is not validated. The claim "same test runs across all three levels" is incomplete without PIL working. |
| Fix | Implement PIL transport in conftest.py. RPi flashes target via OpenOCD, stimulates via CAN, reads responses via semihosting UART. pytest --target=pil selects this transport automatically. |
| Tools | OpenOCD 0.12.x, STM32H7 semihosting, python-can, existing PCAN-USB FD |
| Effort | 1 week ¦ Reusable: Yes — PIL fixture reused for every STM32/TMS570 project |

| GAP-04 | Os_Cfg / NvM_Cfg / WdgM_Cfg Generators | P2 — High | Planned |
| --- | --- | --- | --- |

| Layer | L3 — BSW Codegen |
| --- | --- |
| Problem | Current arxmlgen generates CanIf, Com, PduR, E2E, RTE, and SWC configs. OS configuration (Os_Cfg.h), NvM (non-volatile memory), and WdgM (watchdog manager) generators are missing. These are required for a complete AUTOSAR BSW. |
| Impact | Generated BSW is incomplete for production-grade ECU. OS and watchdog config must be hand-written per project, breaking the automated pipeline promise. |
| Fix | Add three new generators: os_cfg.py (task definitions, alarms, resources from ARXML OsTask elements), nvm_cfg.py (block definitions from NvMBlockDescriptor), wdgm_cfg.py (supervised entity config). |
| Tools | Existing arxmlgen architecture + Jinja2 templates. AUTOSAR Os/NvM/WdgM schema. |
| Effort | 2–3 weeks ¦ Reusable: Yes — generators reused for every Classic AUTOSAR project |

| GAP-05 | XCP Measurement & Calibration | P2 — High | Planned |
| --- | --- | --- | --- |

| Layer | L6 — HIL |
| --- | --- |
| Problem | No XCP slave on ECU firmware and no XCP master on HIL host. Internal ECU variables (PID states, filter outputs, fault counters) are invisible during test execution. Calibration parameters cannot be changed at runtime. |
| Impact | HIL tests can only verify CAN-visible behavior. Internal state debugging requires reflash cycles. Cannot perform model-based calibration workflows. Gap vs CANape is 0% coverage. |
| Fix | Part 1: Integrate Vector XCPlite (open source C) as XCP slave on STM32H7 / TMS570, compile-flag gated. Part 2: Wire pyxcp as pytest fixture on RPi (XCP master over CAN). Part 3: Build A2L generator from ELF DWARF via pyelftools + pya2ldb. |
| Tools | XCPlite (Vector open source), pyxcp, pyelftools, pya2ldb, python-can CAN transport |
| Effort | 5–7 weeks ¦ Reusable: Yes — all three parts fully reusable across projects |

| GAP-06 | SonarQube / SonarCloud Dashboard | P2 — High | Planned |
| --- | --- | --- | --- |

| Layer | CI / Quality |
| --- | --- |
| Problem | MISRA config exists (misra.json, suppressions.txt) and gcov/lcov coverage is generated in SIL. But results are not surfaced in a persistent quality dashboard. Coverage trends over time are not visible. |
| Impact | No single-URL quality gate for portfolio demonstration. Cannot track coverage regression across sprints. MISRA violations not aggregated across all ECU source files. |
| Fix | Connect SonarCloud (free for public repos) to GitHub Actions. Feed lcov XML and cppcheck MISRA XML as CI artifacts. Add sonar-project.properties to repo root. |
| Tools | SonarCloud (free), sonar-scanner, existing gcov/lcov + cppcheck output |
| Effort | 2–3 days ¦ Reusable: Yes — same sonar-project.properties template for all projects |

| GAP-07 | LIN Restbus Simulation | P2 — High | Planned |
| --- | --- | --- | --- |

| Layer | L6 — HIL |
| --- | --- |
| Problem | MCP2003B LIN transceivers are in the BOM but no LIN restbus driver exists. hil_restbus.py covers CAN only. LIN nodes in the 7-ECU topology have no simulation counterpart. |
| Impact | ECUs with LIN interfaces cannot be fully tested. 40% of body domain ECUs (mirrors, window lifters, seats) use LIN. HIL coverage for these is zero. |
| Fix | Implement LIN master state machine on STM32H7 USART + MCP2003B. Add lin_restbus.py companion script to hil_restbus.py. Support LIN 2.1 schedule tables loaded from LDF file. |
| Tools | STM32H7 USART, MCP2003B (already in BOM), python-lin or custom LDF parser |
| Effort | 2–3 weeks ¦ Reusable: Yes — LIN restbus reused for any LIN-capable ECU project |

| GAP-08 | Capella MBSE System Model | P3 — Medium | Planned |
| --- | --- | --- | --- |

| Layer | L1 — System Model |
| --- | --- |
| Problem | DBC is used as the system signal database but there is no formal system model (SysML / MBSE). Interface definitions, component decomposition, and operational analysis are not captured in a portable model. |
| Impact | Cannot export SysML XMI for Simulink / Rhapsody import. System-level architecture is implicit in code, not in a model that can be shared with OEM systems engineers. |
| Fix | Create Capella project with operational analysis, system analysis (3-ECU → 7-ECU topology), and logical architecture. Export SysML XMI. Feed interface definitions into ARXML generator. |
| Tools | Capella MBSE (free Eclipse-based), SysML XMI export |
| Effort | 3–4 weeks ¦ Reusable: Yes — Capella templates reusable for zonal architecture modeling |

| GAP-09 | Automotive Ethernet / DoIP | P3 — Medium | Planned |
| --- | --- | --- | --- |

| Layer | L6 — HIL |
| --- | --- |
| Problem | No 100BASE-T1 PHY interface in current BOM. DoIP diagnostic sessions (over Ethernet) are not possible. Next-generation gateway and ADAS ECUs increasingly use Ethernet as primary backbone. |
| Impact | Cannot test DoIP UDS sessions. Gateway ECUs routing CAN-to-Ethernet are partially testable only. Growing blind spot as industry moves toward zonal Ethernet architectures. |
| Fix | Add RPi CM4 + Waveshare carrier + NXP TJA1101 100BASE-T1 PHY board (~€215 from existing BOM). Configure Open-AVB / gPTP for time sync. Use python-doip for diagnostic sessions. |
| Tools | RPi CM4, TJA1101 PHY eval board, python-doip, python-udsoncan over DoIP |
| Effort | 2–3 weeks hardware + software ¦ Reusable: Yes — DoIP fixture reused for gateway / ADAS ECU projects |

| GAP-10 | MC/DC Coverage for ASIL D | P3 — Medium | Planned |
| --- | --- | --- | --- |

| Layer | CI / Quality |
| --- | --- |
| Problem | gcov provides statement and branch coverage. ASIL D requires MC/DC (Modified Condition/Decision Coverage). Standard gcov does not measure MC/DC. No MC/DC report is currently generated. |
| Impact | Cannot produce ISO 26262 Part 6 structural coverage evidence for ASIL D. MC/DC is mandatory for software unit testing at ASIL D — this is a compliance gap. |
| Fix | Evaluate LLVM source-based coverage (llvm-cov) which reports MC/DC natively since LLVM 17. Alternatively, use gcovr with MC/DC plugin. Add MC/DC report to CI artifacts and SonarQube. |
| Tools | LLVM 17+ / clang, llvm-cov, gcovr, or commercial PC-lint Plus |
| Effort | 1–2 weeks ¦ Reusable: Yes — same coverage pipeline for all ASIL C/D projects |

| GAP-11 | A2L / DCM Calibration File Generation | P4 — Low | Planned |
| --- | --- | --- | --- |

| Layer | L3 — BSW Codegen |
| --- | --- |
| Problem | No A2L generator exists. Calibration parameters in source code have no machine-readable description file. Cannot connect INCA or CANape (or pyxcp) without an A2L. |
| Impact | Dependent on GAP-05 (XCP). Without A2L, XCP is limited to raw address access. Calibration engineers at OEM/Tier-1 expect A2L as a deliverable alongside the ECU binary. |
| Fix | Build A2L generator: parse ELF DWARF via pyelftools, extract __attribute__((section(".cal"))) tagged variables, generate ASAM MCD-2 MC compliant A2L using pya2ldb. Run as post-build CI step. |
| Tools | pyelftools, pya2ldb (christoph2), ARM GCC ELF output |
| Effort | 2–3 weeks (partly overlaps GAP-05) ¦ Reusable: Yes — auto-generated per build, zero per-project effort after initial setup |

| GAP-12 | Public GitHub Repository + Demo Video | P4 — Low | Planned |
| --- | --- | --- | --- |

| Layer | Docs / Portfolio |
| --- | --- |
| Problem | The platform exists as a private repo. No public README, no architecture diagrams in the repo, no demo showing the 7-ECU mixed HIL in operation. |
| Impact | Portfolio value is zero externally. Hiring managers and potential customers cannot evaluate the work without a live demo or public artifacts. |
| Fix | Create public github.com/taktflow repo with: README covering pipeline, architecture SVG diagram, 3-min demo video (candump + fault injection + pytest report), and sanitized golden reference outputs. |
| Tools | GitHub, OBS Studio (recording), draw.io or Excalidraw (diagrams) |
| Effort | 1 week ¦ Reusable: N/A — one-time documentation effort |

# 4. Closure Roadmap

Gaps are sequenced into four phases based on dependencies, priority, and effort. P1 gaps block downstream work and must be closed first. XCP (GAP-05) is deliberately deferred to Phase 3 because it is a standalone module that does not block other gaps, and its reusability value compounds after the rest of the platform is stable.

| Phase 1 | Foundation Closed | Now — 4 weeks |
| --- | --- | --- |
| Gaps | - GAP-01 — ReqIF requirements layer - GAP-02 — ARXML XSD CI gate (hard gate) - GAP-03 — PIL transport adapter | Outcome Full SIL → PIL → HIL pipeline with traceability. ARXML compliance guaranteed per commit. ISO 26262 evidence chain structurally complete. |

| Phase 2 | Quality & Observability | 4 — 10 weeks |
| --- | --- | --- |
| Gaps | - GAP-04 — Os/NvM/WdgM BSW generators - GAP-06 — SonarCloud dashboard - GAP-07 — LIN restbus - GAP-10 — MC/DC coverage | Outcome Complete AUTOSAR BSW codegen. Quality dashboard live. LIN-capable ECUs testable. ASIL D structural coverage evidence available. |

| Phase 3 | Calibration & Observability | 10 — 17 weeks |
| --- | --- | --- |
| Gaps | - GAP-05 — XCP slave + master + pyxcp fixture - GAP-11 — A2L generator from ELF | Outcome Internal ECU state visible during test. Calibration parameters writable at runtime from pytest. Closes the last major gap vs CANape for development workflows. |

| Phase 4 | Platform Expansion | 17 — 24 weeks |
| --- | --- | --- |
| Gaps | - GAP-08 — Capella MBSE system model - GAP-09 — Automotive Ethernet / DoIP - GAP-12 — Public repo + demo video | Outcome Full system model in Capella. Ethernet ECUs testable. Platform publicly demonstrable as open-source SDV reference architecture. |

# 5. Reusability Matrix

Every gap fix produces an artifact. This section maps which artifacts are reusable as platform modules across future ECU projects versus one-time investments.

| Gap | Artifact Produced | Reuse Mechanism | Per-Project Cost | Compounds After |
| --- | --- | --- | --- | --- |
| GAP-01 | reqif/ template + traceability scripts | Copy template, populate req IDs | 1–2 days | Project 2 onward |
| GAP-02 | validate_arxml.py CI step | Include in any ARXML-generating repo | Zero | Immediate |
| GAP-03 | PIL transport conftest.py fixture | Import fixture, configure target | Zero | Project 2 onward |
| GAP-04 | Os/NvM/WdgM generator modules | Add to arxmlgen, configure per schema | < 1 day | Project 2 onward |
| GAP-05 | XCPlite slave module + pyxcp fixture | Add slave to BSP, import fixture | 2–3 days | Project 2 onward |
| GAP-06 | sonar-project.properties template | Copy + configure project key | Half day | Immediate |
| GAP-07 | lin_restbus.py + STM32 LIN driver | Import script, load LDF schedule | 1 day | Project 2 onward |
| GAP-08 | Capella project template | Copy template, populate topology | 1 week modeling | Project 3 onward |
| GAP-09 | DoIP pytest fixture | Import fixture, configure ECU IP | Zero | Project 2 onward |
| GAP-10 | LLVM MC/DC CI step | Enable in CMakeLists.txt | Zero | Immediate |
| GAP-11 | A2L generator (ELF → A2L) | Add post-build step to CMake | Zero | Immediate |
| GAP-12 | README + demo template | Clone and adapt for project | Half day | Project 2 onward |

The economic model: 24 weeks of investment on Project 1 reduces per-project setup cost to < 1 week on every subsequent project. By Project 3 the platform is net-positive compared to purchasing and configuring commercial tooling per project.

# 6. Gap Dependencies

Some gaps must be closed in order. The dependency chain below identifies which gaps block others.

| Gap | Depends On | Reason |
| --- | --- | --- |
| GAP-01 | Nothing | Independent — can start immediately |
| GAP-02 | Nothing | Independent — autosar-data already works in prototype |
| GAP-03 | GAP-02 | PIL transport should run against schema-validated ARXML builds only |
| GAP-04 | GAP-02, GAP-03 | New generators must pass ARXML validation and be testable in PIL |
| GAP-05 | GAP-03 | XCP pytest fixture uses PIL/HIL transport infrastructure |
| GAP-06 | GAP-03 | SonarQube needs SIL + PIL coverage data merged to be meaningful |
| GAP-07 | GAP-03 | LIN restbus needs PIL/HIL transport to test against real ECU |
| GAP-08 | Nothing | Independent — Capella modeling is offline, no code dependency |
| GAP-09 | GAP-03 | DoIP fixture uses same HIL transport layer |
| GAP-10 | GAP-02, GAP-03 | MC/DC meaningful only when SIL + PIL both running |
| GAP-11 | GAP-05 | A2L generator is part of XCP workflow — deploy together |
| GAP-12 | All others | Demo video needs working platform — document last |

Document version 1.0  |  March 2026  |  Taktflow SDV Platform